## Sheet 1
WORK IN PROGRESS
2018-12-31
[11 empty] | COSTS AND | BILLINGS IN |  |  |  | TWELVE MONTHS ENDED DECEMBER 31, 2018 |  |  | PRIOR TO JANUARY 1, 2018
[11 empty] | ESTIMATED | EXCESS OF
| TOTAL | TOTAL | ESTIMATED | TOTAL | TOTAL | TOTAL | TOTAL | COSTS | PERCENTAGE |  | EARNINGS | COSTS AND |  | COST OF
| CONTRACT | COST AT | GROSS | LABOR | MATERIAL | SUB | OTHER | INCURRED | OF | BILLINGS | IN EXCESS | ESTIMATED | REVENUE | REVENUE | GROSS |  |  | GROSS |  |  | GROSS
CONTRACT | AMOUNT | COMPLETION | PROFIT | COSTS | COSTS | COSTS | COSTS | TO DATE | COMPLETION | TO DATE | OF BILLINGS | EARNINGS | EARNED | EARNED | PROFIT | REVENUE | COSTS | PROFIT | REVENUE | COSTS | PROFIT
Project #1 | 1000000 | 900000 | 100000 | 100000 | 200000 | 100000 | 50000 | 450000 | 50% | 550000 | 0 | 50000 | 500000 | 450000 | 50000 | 500000 | 450000 | 50000 | 0 | 0 | 0
Project #2 | 500000 | 350000 | 150000 | 50000 | 50000 | 100000 | 25000 | 225000 | 64.29% | 300000 | 21429 | 0 | 321429 | 225000 | 96429 | 321429 | 225000 | 96429 | 0 | 0 | 0
Project #3 | 750000 | 700000 | 50000 | 50000 | 25000 | 450000 | 60000 | 585000 | 83.57% | 675000 | 0 | 48214 | 626786 | 585000 | 41786 | 626786 | 585000 | 41786 | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0
TOTAL IN PROGRESS | 2250000 | 1950000 | 300000 | 200000 | 275000 | 650000 | 135000 | 1260000 |  | 1525000 | #DIV/0! | #DIV/0! | #DIV/0! | 1260000 | #DIV/0! | #DIV/0! | 1260000 | #DIV/0!
TOTAL CLOSED JOBS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 2250000 | 1950000 | 300000 |  |  |  |  | 1260000 |  | 1525000 | #DIV/0! | #DIV/0! | #DIV/0! | 1260000 | #DIV/0! | #DIV/0! | 1260000 | #DIV/0!